## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
E01a | add new customer | As a Bank Employee, I want to obtain a customer's name, address and date of birth and then verify the details provided. Once verified, I can enter the details to the system, so that I can add new customer to the system and request credit check. | 2 | 2 | 1. Verify that the customer does not exist in system 2. Make sure the customer credit status is recorded as unknown |  | 2019-04-01 | 2019-04-03
E01b | confirm credit status | As a Bank Employee, I want update customer credit status as satisfactory once I receive the conformation from credit agency following a credit check. So that I can carry on to open the account. | 4 | 4 | 1.Verify that customer exists in system matching details given |  | 2019-04-15 | 2019-04-16
E01c | create account | As a Bank Employee, I want to create an account of the type chosen for an existing customer, generate a unique account number and PIN. So that I can open the account and notify customer of account number and PIN. | 2 | 2 | 1. Verify that customer exists in system matching details given 2. Make sure that customer's credit status has been recorded as satisfactory 3. Verify that account of required type is created 4. Verify that account number is unique 5. Verify that PIN is 6 digits |  | 2019-04-04 | 2019-04-05
E02a | deposit cash | As a Depositor, I want to supply the account number and the amount of cash to be deposited. So that I can deposit funds to the account. | 1 | 1 | 1. Verify that account exists matching account number 2. Verify that the account is not inactive or suspended, otherwise return funds to depositor 3. Make sure that the result is shown to depositor 4. Make sure that deposit is marked as cleared |  | 2019-03-18 | 2019-03-19
E02b | deposit cheque | As a Depositor, I want to supply the account number and the amount of cheque to be deposited. So that I can deposit funds to the account. | 1 | 1 | 1. Verify that account exists matching account number 2. Verify that the account is not inactive or suspended, otherwise return funds to depositor 3. Make sure that the result is shown to depositor 4. Make sure that deposit is marked as uncleared |  | 2019-03-18 | 2019-03-19
E03a | clear funds | As an external bank clearing system, I want periodically clears un-cleared funds. So that the funds are credited to the account. | 3 | 3 | 1. Make sure that all the account to be cleared is not been suspended or closed 2. Make sure the clear function is applied to all existed account 3. Make sure the amount of uncleared is added to the balance |  | 2019-04-08 | 2019-04-09
E04a | withdraw saver account | As a customer, I want to supply my account number, the correct PIN, and the saver amount to be withdrawn. So that I can withdraw funds from my account. | 1 | 1 | 1. Verify that account exists matching account number 2. Verify that the account is not inactive or suspended, otherwise return funds to depositor 3. Verify that the pin is correct to the account 4. Make sure that notice amount and date is preset 5. Make sure that the notice date is same as today's date 6. Make sure that the amount to be withdrawn is smaller than the account balance 7. Make sure the result is shown to the customer |  | 2019-03-20 | 2019-03-22
E04b | withdraw junior account | As a customer, I want to supply my account number, the correct PIN, and the junior amount to be withdrawn. So that I can withdraw funds from my account. | 1 | 1 | 1. Verify that account exists matching account number 2. Verify that the account is not inactive or suspended, otherwise return funds to depositor 3. Verify that the pin is correct to the account 4. Make sure that the amount to be withdrawn is smaller than the account balance 5. Make sure the result is shown to the customer |  | 2019-03-20 | 2019-03-22
E04c | withdraw current account | As a customer, I want to supply my account number, the correct PIN, and the currentamount to be withdrawn. So that I can withdraw funds from my account. | 1 | 1 | 1. Verify that account exists matching account number 2. Verify that the account is not inactive or suspended, otherwise return funds to depositor 3. Verify that the pin is correct to the account 4. Make sure that the amount to be withdrawn is smaller than the sum of account balance and overdraft limit 5. Make sure first substract the account balance and then comes to overdraft 6. Make sure the result is shown to the customer |  | 2019-03-20 | 2019-03-22
E05a | check account balance | As a customer, I want to supply my account number, the correct PIN to check this account balance, so that I can make sure the amount withdrawed smaller than balance. | 3 | 3 | 1. Verify that account exists matching account number 2. Verify that the pin is correct to the account 3. Make sure that the balance, uncredited amount and the overdraft limit is shown to the customer |  | 2019-04-10 | 2019-04-12
E06a | suspend account | As a Bank Employee, I want to supply the account number to suspend an account. So that no further transactions may occur until the account is re- instated. | 4 | 4 | 1. Verify that account exists matching account number 2. Make sure the account is not closed |  | 2019-04-16 | 2019-04-17
E06b | reinitiate account | As a Bank Employee, I want to supply the account number to reinitaite an account. So that this account is able to make transactions again | 4 | 4 | 1. Verify that account exists matching account number 2. Make sure the account is not closed |  | 2019-04-17 | 2019-04-18
E07a | close account | As a Bank Employee, I want to supply the account number to check if the account balance is zero when I receive the instruction from the customer to close the account. So that I can close the account. | 4 | 4 | 1. Verify that account exists matching account number 2. Verify that the balance of account is zero 3. Make sure that the balance is not active and can not be reopen again |  | 2019-04-18 | 2019-04-19